## Risks
Risk ID | Title | Description | Category | Likelihood (1-5) | Consequence (1-5) | Risk Score | Mitigation | Owner | Status
R-001 | Battery Endurance Shortfall | Measured endurance may not meet the 25-minute requirement under hot conditions. | Technical | 3 | 4 | 12 | Qualify higher energy density cells, optimize propeller selection. | AV Lead | Open
R-002 | EMI on Datalink | Urban EMI environments may reduce video link performance. | Technical | 2 | 4 | 8 | Perform EMI testing, add frequency-hopping configuration. | Comm Lead | Open
R-003 | GCS UI Complexity | GCS interface may be too complex for dismounted soldier use. | User/UX | 3 | 3 | 9 | Iterate UI with soldier feedback, simplify control modes. | PM | In Work
R-004 | Integration Schedule Creep | Subsystem integration tasks may slip due to late hardware deliveries. | Schedule | 4 | 3 | 12 | Stage integration by subsystem, reserve lab time, add integration buffer. | IVVQ Lead | Open