## WBS
WBS ID | Level | Element Name | Description | Owner | Start Date | Finish Date | % Complete
1.0 | 1 | FalconEye Program | Overall program | PM | 2025-01-01 | 2025-12-31 | 35
1.1 | 2 | System Engineering | System requirements and architecture | SE Lead | 2025-01-01 | 2025-06-30 | 60
1.1.1 | 3 | Requirements Definition | Capture and baseline system requirements | SE1 | 2025-01-01 | 2025-03-31 | 90
1.1.2 | 3 | Architecture & ICDs | Define interfaces and architecture diagrams | SE2 | 2025-02-01 | 2025-05-31 | 45
1.2 | 2 | Air Vehicle | Airframe, propulsion, avionics | AV Lead | 2025-01-15 | 2025-09-30 | 40
1.2.1 | 3 | Airframe | Structure, weight, materials | ME1 | 2025-01-15 | 2025-06-30 | 55
1.2.2 | 3 | Avionics | Flight controller and sensors | EE1 | 2025-02-01 | 2025-08-31 | 35
1.3 | 2 | Payload | EO/IR gimbal and stabilization | Payload Lead | 2025-02-01 | 2025-09-30 | 30
1.4 | 2 | GCS & Datalink | Ground station HW/SW and RF link | Comm Lead | 2025-02-15 | 2025-10-31 | 25
1.5 | 2 | Integration & Test | System integration and verification testing | IVVQ Lead | 2025-05-01 | 2025-12-15 | 10